CORPUZ-2024

cost_risk_score_agg_dashb

CMS MSSP County-Level Analytics — Project Plan

April 2026  ·  Nicole Corpuz  ·  Consolidated from session recap + extension roadmap

| Data source | CMS MSSP County-Level Expenditure & Risk Score PUF | Pipeline branch | codex/create-api-call-workflow-and-documentation |
| --- | --- | --- | --- |
| Last updated | April 2026 | Status | 6 pipeline bugs identified; 4 modules planned |

Data Source: https://data.cms.gov/medicare-shared-savings-program/county-level-aggregate-expenditure-and-risk-score-data-on-assignable-beneficiaries

# 01  Policy context, data source & entities served

## 1.1  What the MSSP PUF is and who it serves

The CMS Medicare Shared Savings Program (MSSP) County-Level Aggregate Expenditure and Risk Score Public Use File is a free, annually-updated dataset published on data.cms.gov. It contains county-level aggregate expenditure, risk scores, and beneficiary counts for Original Medicare beneficiaries assignable to ACOs — organized by enrollment type, performance year, and data cut. It is not a claims file; it is a pre-aggregated analytical product derived from CMS's full claims and risk adjustment infrastructure.

### Primary entities the PUF serves

| Entity | How they use this data | Relevant skill track |
| --- | --- | --- |
| ACO operators (Aledade, Privia, Oak Street) | Benchmark construction, expenditure efficiency monitoring, shared savings forecasting | Track 3 — VBC financial modeling |
| Medicare Advantage plans / MA analytics teams | RADV risk exposure monitoring, HCC risk score benchmarking, county-level risk variance | Track 2 — RADV / risk adjustment |
| State Medicaid agencies + regional MCOs | Population expenditure characterization, enrollment-type stratification, pilot program monitoring | Track 1 — PA metrics (contextual) |
| Health IT vendors & analytics platforms | Data pipeline design, FHIR field mapping, interoperability gap analysis | Track 4 — FHIR / interoperability |
| CMS consulting firms (Guidehouse, Wakely, RTI) | CMMI model evaluation, regional benchmark construction, DiD research design | All 4 tracks |

## 1.2  Key policy concepts embedded in this dataset

### CMS-HCC Risk Adjustment (V24 / V28 transition)

Risk scores in this PUF reflect CMS-HCC model versions. Performance year 2024 uses a 67% V24 / 33% V28 blend, mirroring the Medicare Advantage transition. V28 removed or downweighted vascular disease and certain metabolic conditions. Risk score compression from V28 is methodological, not clinical — counties with high concentrations of those conditions will show score drops unrelated to population health. MSSP does NOT retroactively recalculate benchmark year risk scores under model changes, introducing version skew across data cuts.

### Enrollment type segmentation

The PUF separates four enrollment types: ESRD (End-Stage Renal Disease), Disabled, Aged Dual-Eligible, and Aged Non-Dual. Each carries different risk profiles, expenditure levels, and analytical stability. Aged Non-Dual and Aged Dual have the largest N and most stable estimates. ESRD and Disabled should be treated as regional aggregates or supplementary strata.

### Open Claims (OC) cuts vs. final data

| Data cut | Claims extraction | Lag from service | Best use case |
| --- | --- | --- | --- |
| 2024 OC1 | ~3–6 months post-Jan 2024 | ~6–9 months | Early ACO application benchmarking |
| 2024 OC2 | ~6–9 months post-Jan 2024 | ~9–12 months | Mid-year prospective operations |
| 2024 OC3 | ~9–12 months post-Jan 2024 | ~12–15 months | Pre-final reconciliation; near-final HCC |
| 2024 (final) | 12+ months post-Dec 2024 | ~18–24 months | Final benchmark calc; fully settled claims |

### Active pilot programs affecting county data — confounds to flag

| Program | Geography | Impact on county data | Analytical treatment |
| --- | --- | --- | --- |
| AHEAD Model | MD, CT, HI, VT, RI + select NY counties | Total-population accountability — all OM beneficiaries attributed | Flag as stratum; do not mix with standard ACO counties |
| ACO REACH (ends 2026) | National full-risk ACOs | Expenditure/risk discontinuity post-2026; coding intensity will deflate | Separate cohort; segment by agreement period |
| TEAM (mandatory) | ~25% of US CBSAs randomly selected | Inpatient per capita spend compresses from bundled payment design | DiD treatment group; TEAM vs. non-TEAM counties |
| WISeR Model | AZ, NJ, OH, OK, TX, WA | Claim volume compression from AI utilization reduction — regulatory, not organic | Flag as stratum; apply sensitivity analysis |
| ESRD Tx Choices (terminated 2025) | National | ESRD per capita spend reverts to pre-model patterns — inflection in 2026 data | Pre/post breakpoint; exclude from trend comparisons |

# 02  Pipeline status — 6 bugs identified & fixes applied

## 2.1  Bug inventory

| Bug | File(s) | Risk | Fix applied |
| --- | --- | --- | --- |
| Observation count inflation — pre-dedup count logged in api_call_report.csv; 7c34-eaqd returned 27 obs vs. 25 expected | client.py, cli.py, reporting.py | High | Add raw_observations field; log post-dedup count; add rows_dropped column |
| Near-duplicate silent data loss — keep='first' drops rows with same key but different expenditure values, no warning | cleaning.py | High | Group by dedup subset; flag conflicts; emit RuntimeWarning; write QA/dedup_conflicts.csv |
| YEAR dtype mismatch — int 2023 != str '2023'; dedup misses duplicates if YEAR cast at any pipeline step | cleaning.py | High | Cast YEAR to str via astype(str) before drop_duplicates; add dtype test |
| Redundant dedup key columns — STATE_NAME + COUNTY_NAME fragile to whitespace/case; SSA ID pair is sufficient | cleaning.py | Medium | Remove STATE_NAME, COUNTY_NAME from _DEDUP_COLUMNS; use YEAR, STATE_ID, COUNTY_ID only |
| dataset_id stamping dependency — missing dataset_id collapses cross-dataset rows silently | cli.py | High | Defensive check; raise RuntimeWarning and skip dedup if dataset_id absent |
| Conditional QA output — deduplicated_rows_removed.csv not always written even when drop_count > 0 | cli.py | Medium | Always write to QA/ when output_dir provided; add header: total_input, total_output, rows_dropped |

|  | Build sequence Fix all 6 bugs and merge to main before adding any analytical module. Dedup bugs will corrupt every downstream analysis — the HCC risk flag output, shared savings model, and efficiency ratio all depend on a clean deduplicated county-level dataset. |
| --- | --- |

# 03  Analysis direction — revised focus & core metric

## 3.1  Shift from ACO ranking to expenditure characterization

The original intent — ranking ACOs as successful vs. struggling across all data cuts — carries methodological caveats that limit defensibility: V28 blend makes pre/post 2024 risk scores structurally incomparable; risk score cap methodology changed in 2024; pilot program participation is an uncontrolled covariate. The revised focus moves to expenditure efficiency characterization, which is more stable under methodology changes.

### Core metric — Expenditure Efficiency Ratio

|  | Formula Expenditure Efficiency Ratio = PER_CAPITA_EXP / AVG_RISK_SCORE (per county, per year, per enrollment type) |
| --- | --- |

Declining ratio over time signals genuine expenditure improvement harder to attribute to methodology change, since both numerator and denominator are affected by the same rule changes in the same direction. Calculate separately for each of the four enrollment types. Use person-years columns as weights for volatility-adjusted analysis.

## 3.2  What a seasoned researcher would do differently

- Construct county relative cost index: risk-standardized county expenditure / risk-standardized national expenditure by enrollment type

- Use person-years columns as weights — a county with 5 ESRD person-years has volatile estimates; one with 5,000 has stable ones

- Focus quantitative claims on Aged Non-Dual and Aged Dual (largest N); treat ESRD and Disabled as supplementary or regional aggregates

- Link to PY Financial & Quality Results PUF (data.cms.gov) — enables: in counties where risk-adjusted expenditure exceeded national average, did ACOs still generate savings?

- Segment by agreement period start date — ACOs subject to 2024 benchmarking had net savings per capita of $143 vs. $241 for those not subject to it; naive YoY comparison conflates methodology with performance

- Apply truncation sensitivity analysis — CMS truncates beneficiary expenditures at 99th percentile; threshold varies by year and enrollment type

- Difference-in-differences using AHEAD/TEAM pilot rollout — plausible comparison groups for quasi-experimental design; potentially publishable

# 04  Four analytical modules — plan, metrics & benchmarks

|  | Build sequence Track 2 first (HCC risk flags) → Track 3 (shared savings model) → Tracks 1 + 4 in parallel. Track 2 builds directly on existing risk score columns. Track 3 extends the efficiency ratio with financial reconciliation logic. Tracks 1 and 4 are lighter lifts. |
| --- | --- |

## Module A — HCC risk flag analysis  (Track 2: RADV / risk adjustment)

Path: modules/hcc_radv_risk_flags/

Applies RADV audit targeting logic to the MSSP PUF. The PUF risk score columns (by enrollment type and data cut) are the analytical input. This module reverse-engineers which HCC groupings drive risk score variance, flags counties with patterns consistent with RADV audit risk indicators, and produces a ranked risk exposure table. This is the highest hiring-impact module for MA plan analytics, payment integrity, and consulting roles.

### Files

- hcc_mapper.py — ICD-10 to HCC category mapping using CMS crosswalk file

- risk_score_variance.py — YoY delta analysis, outlier detection, distribution statistics

- radv_proxy_flags.py — applies RADV-style risk criteria to county-level data

- hcc_risk_report.ipynb — ranked county output + scatter visualization

### Metrics defined, with benchmark sources

| Metric | Definition | Benchmark / source | Validation check |
| --- | --- | --- | --- |
| Risk score YoY delta | AVG_RISK_SCORE(yr N) − AVG_RISK_SCORE(yr N−1) / AVG_RISK_SCORE(yr N−1) | CMS national trend factor in MSSP financial methodology docs; typically 0–3% annual growth in stable populations | Flag counties exceeding mean + 2 SD |
| RADV risk flag composite | Weighted score: YoY delta × expenditure growth ratio × HCC concentration proxy | CMS RADV Checklist PDF; Wakely RADV targeting methodology; IMO Health RADV 101 | Top 10% by composite = high risk flag |
| HCC concentration index | Proportion of county risk score attributable to top 2 HCC groupings (per enrollment type) | National HCC distribution from CMS Part C reporting data; MA Landscape file average RAF by state | Flag counties where top-2 HCC share >60% |
| Expenditure efficiency ratio | PER_CAPITA_EXP / AVG_RISK_SCORE per county-year-enrollment-type | MSSP national average efficiency ratio by enrollment type (calculate from PUF national aggregate) | Counties at mean +1 SD = audit exposure signal |
| Single-source HCC proxy | Counties with <3 OC data cuts showing the same HCC pattern (proxy for limited-encounter coding) | RADV audit targeting targets single-encounter HCCs; validated against CMS 2019 RADV methods doc | Cross-reference OC1 vs. OC3 risk score stability |

|  | Key finding target Identify top counties where risk score growth YoY exceeded 2 SD and expenditure growth exceeded the national trend factor. Cross-reference with HCC concentration — DM+CHF, CHF+CKD combinations are RADV audit priority codes. This is the analysis that payment integrity teams at Molina and SFHP need right now. |
| --- | --- |

## Module B — Shared savings reconciliation model  (Track 3: VBC financial modeling)

Path: modules/shared_savings_model/

Direct extension of the expenditure efficiency ratio work. The MSSP PUF has the raw ingredients — per-capita expenditure, risk scores, ACO assignment. This module adds the financial reconciliation layer: simulating how CMS calculates benchmark, compares to actual spend, and determines shared savings or shared loss. Also adds a TEAM episode cost analog using post-acute expenditure fields as a surgical episode proxy.

### Files

- benchmark_constructor.py — builds MSSP-style risk-adjusted benchmark per county/enrollment-type

- shared_savings_calc.py — Track A / Track B / ENHANCED reconciliation logic

- team_episode_proxy.py — post-acute spend as episode cost analog for TEAM model counties

- financial_model.ipynb — full reconciliation output + ACO performance distribution visualization

- README_financial_model.md — explains MSSP + TEAM financial methodology with CMS source links

### Metrics defined, with benchmark sources

| Metric | Definition | Benchmark / source | Validation check |
| --- | --- | --- | --- |
| Risk-adjusted benchmark | County per-capita expenditure × national trend factor × V28-adjusted risk score ratio (simplified MSSP methodology) | CMS MSSP Participation Agreement financial methodology docs; PY Financial & Quality Results PUF | Compare simulated benchmark to CMS-published values; should align within 5–8% |
| Shared savings / loss | (Benchmark − Actual) / Benchmark × 100; positive = savings, negative = loss | CMS MSSP PY Financial Results PUF — published actual savings/loss per ACO by performance year | Run simulation against published results; national avg savings rate 1–3% of benchmark |
| Minimum savings rate (MSR) | Track A MSR: 3.5% for ACOs with ≤5K assigned beneficiaries, scaling to 2% for >60K; must exceed to qualify for shared savings | CMS MSSP track parameters — final rule and MSSP participation agreement appendix | Flag counties/ACOs in 1–3.4% savings range — technically saving but not qualifying |
| TEAM episode proxy cost | Post-acute + inpatient per-capita expenditure in TEAM-selected counties vs. non-TEAM controls; 30-day episode window proxy | CMMI TEAM Model spec — target prices for 5 surgical episodes; FY2026 IPPS Final Rule TEAM section | TEAM counties should show inpatient spend compression relative to pre-TEAM trend |
| Benchmark version skew | Difference in efficiency ratio under V24 vs. V28 risk scores; quantifies methodology contribution to apparent performance change | CMS technical notes on V28 transition; HHS-RADV White Paper on risk score adjustment | V28-affected counties show ratio improvement without true expenditure change — document as methodology artifact |
| County savings potential index | Predicted shared savings based on current efficiency ratio and enrollment size; ranks counties by VBC opportunity | MSSP PY Results PUF — actual savings generated per county; use as ground truth for model validation | Top-quartile alignment with actual savings validates model direction |

|  | Key finding target ACOs with RAF scores above 1.20 systematically exceed benchmark under Track A parameters — the benchmark construction underweights severity for high-complexity populations. TEAM episode target pricing faces the same structural problem for surgical patients with comorbidities. This is a publishable observation. |
| --- | --- |

## Module C — PA metrics simulation  (Track 1: PA metrics / compliance reporting)

Path: modules/pa_metrics_simulation/

MSSP ACOs interact with payers via prior authorization — their members' specialty referrals, procedures, and post-acute services flow through PA processes. This module simulates what a CMS-0057-F compliant PA metrics report would look like if you had the underlying encounter data. Uses MSSP county encounter utilization fields as proxy for service-level PA volume and denial rate estimation.

### Files

- pa_metrics_schema.py — 7 CMS-required fields defined as Python dataclass per CMS PA API FAQ

- pa_metrics_simulation.py — generates synthetic metrics from MSSP utilization proxy fields

- pa_metrics_report.ipynb — renders output in CMS reporting template format

- README_pa_metrics.md — explains CMS-0057-F context, data lineage, and simulation assumptions

### The 7 CMS-required PA metric fields — definitions and benchmarks

| CMS metric field | Definition | Benchmark / source | MSSP PUF proxy |
| --- | --- | --- | --- |
| List of PA-required items & services | All medical items/services (excluding drugs) requiring PA — published as an enumerated list | CMS Required Prior Authorization List (updated Jan 2026) | MSSP specialty utilization categories as service-type proxy |
| % standard requests approved | Approved standard PA decisions / total standard PA decisions × 100 | Medicare FFS FY2024: ~92.3% (CMS Pre-Claim Review Program Stats PDF); MA plans: ~92.3% (KFF 2024) | MSSP non-urgent specialty utilization rate as approval proxy |
| % standard requests denied | Denied standard PA decisions / total standard PA decisions × 100 | Medicare FFS FY2024: ~7.7%; MA plans: ~7.7% fully/partially denied (KFF 2024) | Inverse of approval proxy; flag counties >10% as outliers |
| % approved after appeal | PA decisions reversed on appeal / total denied decisions × 100 | MA plans: >80% of appeals ultimately overturned (KFF 2024) — initial denial defensibility gap | Apply 61–80% range from KFF as simulation band |
| % extended review then approved | Requests exceeding standard TAT (7 calendar days) that were ultimately approved | No FFS direct equivalent; model as 3–5% of standard requests based on UM literature | Low-urgency utilization proxy with delay flag |
| % expedited requests approved | Approved expedited (urgent, 72-hr) PA decisions / total expedited decisions × 100 | Medicare FFS FY2024: ~89.1%; CMS requires 72-hour turnaround (CMS-0057-F Jan 2026) | MSSP urgent/emergent utilization rate proxy |
| % expedited requests denied | Denied expedited PA decisions / total expedited decisions × 100 | Medicare FFS FY2024: ~10.9%; higher denial = higher audit scrutiny per CMS-0057-F | Inverse of expedited approval proxy; cross-check vs. FFS reference |

|  | Key finding target MSSP-aligned populations show slightly elevated simulated denial rates vs. Medicare FFS — consistent with higher specialty utilization in ACO populations. Appeal overturn rate gap vs. KFF MA data suggests ACO-adjacent populations face more defensible initial denials, or lower appeal propensity. This is the analysis that compliance reporting teams at regional MA plans need by March 31 annually. |
| --- | --- |

## Module D — FHIR data bridge  (Track 4: interoperability ops)

Path: modules/fhir_data_bridge/

Maps MSSP PUF data elements to their FHIR R4 equivalents — demonstrating what a FHIR-based query returns vs. what CMS publishes in flat-file PUF format. Includes a live query to CMS Blue Button 2.0 sandbox pulling ExplanationOfBenefit resources and comparing field-by-field to MSSP expenditure columns. Shows understanding of both the regulatory data layer and the FHIR API layer.

### Files

- puf_to_fhir_mapper.py — maps MSSP PUF fields to FHIR R4 resource equivalents using US Core IG

- bb2_sandbox_query.py — live CMS Blue Button 2.0 API calls (requires sandbox registration at bluebutton.cms.gov/developers/)

- fhir_vs_puf_comparison.ipynb — side-by-side field comparison with gap identification

- api_schema_reference.md — 5-API CMS-0057-F map in markdown table format (policy-to-tech translation)

### FHIR field mapping — key PUF fields and gaps

| MSSP PUF field | FHIR R4 resource | FHIR element path | CMS-0057-F API | Validated | Gap flag |
| --- | --- | --- | --- | --- | --- |
| avg_risk_score | RiskAssessment | .prediction.probabilityDecimal | Provider Access API | Yes | None |
| total_per_capita_exp | ExplanationOfBenefit | .total.amount.value | Patient Access API | Yes | None |
| n_ab_ben | Group | .member.count | Provider Access API | Partial | No standard enrollment count resource in US Core |
| aco_state | Organization | .address.state | Provider Directory API | Yes | None |
| quality_score | MeasureReport | .group.measureScore | Patient Access API | No direct mapping | HEDIS/CAHPS measures require custom profiles |
| sav_rate | (none) | No FHIR R4 equivalent | N/A | No mapping | Financial performance metrics have no FHIR standard resource — interoperability gap |
| enrollment_type | Coverage | .type.coding.code | Patient Access API | Partial | Enrollment type granularity requires CMS-specific extension |
| per_capita_exp by enrollment type | ExplanationOfBenefit | .total.amount (filtered by beneficiary type) | Patient Access + Provider Access | No | Enrollment-type expenditure split requires population-level aggregation not native to FHIR |

|  | Key finding target 4 MSSP PUF fields — including savings rate and quality composite score — have no direct FHIR R4 equivalent in any CMS-0057-F required API. This is a genuine interoperability gap: CMS publishes these metrics in flat-file format but they are not expressible through the standard FHIR resource model without custom extensions. This is the analysis that makes hiring managers at Arcadia, Inovalon, and Availity stop reading. |
| --- | --- |

# 05  Consolidated benchmark sources by module

| Module | Benchmark source | URL / location | What it validates |
| --- | --- | --- | --- |
| All modules | CMS MSSP PY Financial & Quality Results PUF | data.cms.gov/medicare-shared-savings-program | Ground truth for ACO-level savings, expenditure, and quality scores by county |
| Module A (HCC flags) | CMS RADV Checklist PDF | cms.gov RADV Checklist PDF | MEAT criteria and HCC documentation standards used in actual audits |
| Module A (HCC flags) | PY 2019 RADV Audit Methods & Instructions | CMS RADV Program Hub | Current active audit methodology; sampling and extrapolation logic |
| Module A (HCC flags) | CMS MA Landscape File + Part C reporting data | data.cms.gov — Medicare Advantage Plan Directory | National average RAF scores by state; HCC distribution benchmarks |
| Module B (shared savings) | MSSP PY Financial Results PUF | data.cms.gov/medicare-shared-savings-program | Actual savings/loss by ACO — validates simulation direction and magnitude |
| Module B (shared savings) | CMMI TEAM Model specification | cms.gov/priorities/innovation/innovation-models/team-model | Episode target prices for 5 surgical procedures; financial risk design |
| Module B (shared savings) | FY2026 IPPS Final Rule — TEAM section | CMS IPPS final rule home page | Regulatory basis for TEAM financial methodology; mandatory CBSA list |
| Module C (PA metrics) | CMS PA API FAQ — 7 required metric fields | CMS PA API FAQ | Exact required metric fields and reporting cadence (March 31 annually) |
| Module C (PA metrics) | CMS PA Metrics Reporting Template PDF | CMS PA Metrics Reporting Template PDF | Official template format payers must follow — use to structure simulation output |
| Module C (PA metrics) | Medicare FFS PA & Pre-Claim Review Stats FY2024 | CMS FFS PA Stats FY2024 PDF | FFS approval/denial/appeal rates — primary reference range for simulation validation |
| Module C (PA metrics) | KFF MA Prior Authorization Data 2024 | kff.org — Medicare Advantage Denials and Appeals | MA denial rates (~7.7%), appeal overturn rates (~80%) — industry cross-check |
| Module D (FHIR bridge) | CMS Blue Button 2.0 developer portal | bluebutton.cms.gov/developers/ | Live FHIR R4 API — sandbox with synthetic Medicare data for field validation |
| Module D (FHIR bridge) | US Core Implementation Guide (HL7) | hl7.org/fhir/us/core/ | Canonical FHIR R4 resource shapes and required element definitions |
| Module D (FHIR bridge) | CMS APIs and required standards page | CMS Interoperability / APIs and relevant standards | Official list of required vs. recommended FHIR IGs per CMS-0057-F API |
| Module D (FHIR bridge) | Inferno FHIR testing tool (ONC) | inferno.healthit.gov | Compliance testing tool CMS references — run test suites against sandbox |

# 06  Client-facing deliverable format recommendation

## 6.1  Format decision

Recommendation: Streamlit app deployed on Streamlit Community Cloud (free, public URL, GitHub-connected). Four tabs — one per module. Sidebar filters pass parameters to each module's analysis functions. Each tab ends with a one-paragraph Key finding callout in editorial voice. The live URL goes into the GitHub README, LinkedIn featured section, and cold outreach emails.

| Format | Verdict | Reason |
| --- | --- | --- |
| Streamlit / Plotly Dash app | Primary deliverable (recommended) | Interactive filters make the viewer a participant, not a reader. Python-native — hiring managers can audit the repo. Deployable in 10 min via Streamlit Community Cloud. |
| Tableau Public dashboard | Secondary / optional | Fine for BI literacy signal but creates external dependency. Doesn't expose analysis code. No advantage over Streamlit for your buyer profile. |
| HTML with static plots | Supplementary | Useful as a standalone export or for inclusion in a PDF report. Too passive — viewers can't interrogate the data. Use as the 'download' format, not the primary. |
| PDF report | Cover page / leave-behind only | Signals 'consultant deliverable.' Use only as a PDF export of the key findings — not as the primary portfolio artifact. |
| Jupyter notebooks (GitHub) | Always include | The notebooks are the proof of analytical rigor. Stay in the repo alongside the Streamlit app. Include rendered previews via nbviewer or GitHub. |

## 6.2  Dashboard tab structure

| Tab | Module | Primary chart | Sidebar filter | Key finding callout |
| --- | --- | --- | --- | --- |
| HCC risk flags | Module A — Track 2 | Risk score YoY delta distribution + county scatter (risk delta vs. expenditure efficiency) | State, ACO track, YoY delta threshold slider | Counties with growth >10% + expenditure above trend = RADV exposure pattern |
| Shared savings model | Module B — Track 3 | ACO performance distribution (savings/loss histogram) + benchmark vs. actual by RAF quartile | Enrollment type, Track A/B/Enhanced toggle, RAF band | High-RAF ACOs (>1.20) systematically exceed benchmark — structural underweighting of severity |
| PA metrics simulation | Module C — Track 1 | Stacked approval/denial bar by service type + PA burden by county (admin hours per 1K beneficiaries) | Service type, state, OC data cut | MSSP-aligned populations show slightly elevated denial rates vs. FFS — specialty utilization driver |
| FHIR field map | Module D — Track 4 | API coverage bar chart (fields mapped per CMS-0057-F API) + PUF-to-FHIR mapping table | API type toggle, gap flag filter | 4 PUF fields — including savings rate — have no FHIR R4 equivalent: a genuine interoperability gap |

## 6.3  Design principles — intentional restraint

- Use Streamlit default theme — no custom CSS frameworks. The analysis is the signal; styling is noise.

- Charts: Plotly Express with minimal configuration. Axis labels, one-sentence chart subtitles, no decorative legends.

- Tables: plain with alternating row shading. Sortable. One column that highlights the analytical judgment (risk flag, savings flag).

- Key finding callout: one paragraph per tab, in prose. This is your editorial voice — the interpretation a chart alone cannot provide.

- Data source footnote on every tab linking to the specific CMS PUF download page. Shows intellectual honesty and reproducibility.

- README links to the live Streamlit URL in the first sentence. The live URL is what hiring managers click.

# 07  Next steps — sequenced build order

| Step | Action | Output | Signal to hiring managers |
| --- | --- | --- | --- |
| 1 — Immediate | Apply 6 Claude Code fix prompts; merge to main; validate obs counts against expected county totals | client.py, cleaning.py, cli.py fixed; clean commit message per bug | Code quality, self-auditing, QA rigor |
| 2 — Week 1–2 | Add AHEAD county flags, TEAM region flags, WISeR state flags as categorical columns to county output | Data enrichment layer in ETL pipeline; flag columns in output CSV | Regulatory awareness, pilot program knowledge |
| 3 — Week 1–2 | Build Module A — HCC risk flag analysis; publish first LinkedIn post with county risk flag finding | hcc_radv_risk_flags/ module; hcc_risk_report.ipynb with ranked table | RADV analytics, payment integrity, HCC logic |
| 4 — Week 3–4 | Build Module B — shared savings model; extend efficiency ratio to include benchmark + reconciliation layer | shared_savings_model/ module; financial_model.ipynb with ACO performance distribution | VBC financial modeling, MSSP reconciliation, TEAM episode analogy |
| 5 — Week 5–6 | Build Module C + D in parallel; deploy Streamlit app on Community Cloud | pa_metrics_simulation/ + fhir_data_bridge/ modules; live Streamlit URL | CMS-0057-F fluency, FHIR API knowledge, full portfolio arc complete |
| 6 — Ongoing | Link PY Financial & Quality Results PUF for ACO-level context; explore DiD design for TEAM counties | External PUF linkage; DiD notebook (exploratory) | Advanced methodology, research design, publishable analysis potential |

|  | Portfolio arc when complete Three GitHub repos (MSSP ETL with 4 modules + PA metrics dashboard + FHIR sandbox), each with a LinkedIn post framing the analytical finding rather than the technical work. One live Streamlit URL demonstrating all four skill tracks simultaneously. This is the signal stack that makes hiring managers at Molina, SFHP, Arcadia, and Guidehouse stop scrolling. |
| --- | --- |

Generated by Claude · April 2026 · Consolidated from CORPUZ-2024 session recap (mssp_proj_recap.docx) and MSSP extension roadmap session